## Executive Summary
Budget Plan: Prototype/Innovation
Generated: 2026-02-05
STORE CONFIGURATION
Store Type: | Prototype/Innovation
Typical Square Footage: | 4,000 sqft
Size Range: | 3,500 - 5,000 sqft
Primary Markets: | Select test markets
Use Cases: | New concept testing, Format innovation, Future rollout development
COST SUMMARY
Category | Amount | % of Total | Cost/SqFt
Construction | 435483 | 35% | 108.8708
Electrical | 149308 | 12% | 37.327
HVAC | 99538 | 8% | 24.8845
Plumbing | 62211 | 5% | 15.5527
Fixtures | 311059 | 25% | 77.7648
Technology | 99538 | 8% | 24.8845
Soft Costs | 87096 | 7% | 21.774
TOTAL PROJECT COST | 1244240 |  | 311.06
Based on 5 historical projects

## Detailed Line Items
Detailed Line Items: Prototype/Innovation
Category | Item | Quantity | Unit | Unit Cost | Total | Source
CONSTRUCTION
| Demolition | 3500 | sqft | 5.5 | 19250 | Cost Model: suburban_standard
| Framing | 3500 | sqft | 12 | 42000 | Cost Model: suburban_standard
| Drywall | 7000 | sqft | 8.5 | 59500 | Cost Model: suburban_standard
| Flooring (LVT) | 3500 | sqft | 18 | 63000 | Cost Model: suburban_standard
| Ceiling | 3500 | sqft | 7.5 | 26250 | Cost Model: suburban_standard
| Paint | 7000 | sqft | 2.25 | 15750 | Cost Model: suburban_standard
| Construction Subtotal |  |  |  | 226625
ELECTRICAL
| 400A electrical panel | 1 | each | 8500 | 8500 | Cost Model: suburban_standard
| LED lighting fixtures | 65 | each | 412 | 26780 | Cost Model: suburban_standard
| Outlets and switches | 85 | each | 125 | 10625 | Cost Model: suburban_standard
| Emergency lighting | 12 | each | 385 | 4620 | Cost Model: suburban_standard
| Electrical rough-in | 3500 | sqft | 7.5 | 26250 | Cost Model: suburban_standard
| Electrical Subtotal |  |  |  | 77700
HVAC
| Commercial HVAC unit (VRF) | 1 | each | 16500 | 16500 | Cost Model: suburban_standard
| Ductwork | 3500 | sqft | 8.5 | 29750 | Cost Model: suburban_standard
| HVAC controls | 1 | system | 3250 | 3250 | Cost Model: suburban_standard
| Installation labor | 1 | system | 2300 | 2300 | Cost Model: suburban_standard
| Hvac Subtotal |  |  |  | 51800
PLUMBING
| Bathroom fixtures | 2 | set | 2850 | 5700 | Cost Model: suburban_standard
| Water heater | 1 | each | 1250 | 1250 | Cost Model: suburban_standard
| Water lines | 280 | lf | 22 | 6160 | Cost Model: suburban_standard
| Drainage | 280 | lf | 28 | 7840 | Cost Model: suburban_standard
| Plumbing labor | 3500 | sqft | 3.25 | 11375 | Cost Model: suburban_standard
| Plumbing Subtotal |  |  |  | 32375
FIXTURES
| Wall display fixtures | 320 | lf | 185 | 59200 | Cost Model: suburban_standard
| Floor fixtures | 45 | each | 725 | 32625 | Cost Model: suburban_standard
| Mannequins | 18 | each | 385 | 6930 | Cost Model: suburban_standard
| Signage package | 1 | package | 12500 | 12500 | Cost Model: suburban_standard
| Checkout counter | 24 | lf | 425 | 10200 | Cost Model: suburban_standard
| Dressing rooms | 8 | each | 1850 | 14800 | Cost Model: suburban_standard
| Mirrors and accessories | 1 | package | 8500 | 8500 | Cost Model: suburban_standard
| Fixtures Subtotal |  |  |  | 161875
TECHNOLOGY
| POS system (3 terminals) | 1 | system | 12500 | 12500 | Cost Model: suburban_standard
| Security cameras | 16 | each | 875 | 14000 | Cost Model: suburban_standard
| WiFi infrastructure | 1 | system | 4250 | 4250 | Cost Model: suburban_standard
| Digital displays | 4 | each | 2150 | 8600 | Cost Model: suburban_standard
| Sound system | 1 | system | 3850 | 3850 | Cost Model: suburban_standard
| Technology wiring | 3500 | sqft | 2.5 | 8750 | Cost Model: suburban_standard
| Technology Subtotal |  |  |  | 51800
SOFT_COSTS
| Architectural design | 1 | project | 15000 | 15000 | Cost Model: suburban_standard
| Engineering | 1 | project | 8500 | 8500 | Cost Model: suburban_standard
| Permits and fees | 1 | project | 6250 | 6250 | Cost Model: suburban_standard
| Project management | 1 | project | 8500 | 8500 | Cost Model: suburban_standard
| Contingency (10%) | 1 | percent | 7075 | 7075 | Cost Model: suburban_standard
| Soft_Costs Subtotal |  |  |  | 45325

## Scenario Comparisons
Budget Scenarios Comparison
Scenario | Description | Total Cost | vs. Base | Notes
Base Case | Standard build, Columbus market, 12-week timeline | 1244240 | 0% | Historical average
Cincinnati Market | Union labor requirements | 1318894 | 6% | Regional modifier: electrical 1.08x, construction 1.05x
Accelerated Schedule | 8-week timeline (vs. 12 weeks) | 1430876 | 15% | Labor premium, expedite fees
Premium Finishes | Upgraded materials and fixtures | 1517972 | 22% | Fixture upgrade 30%, material upgrade 15%
Budget Cap (Value Eng.) | Cost-optimized specifications | 1094931 | -12% | Material substitutions, simplified finishes

## Data Sources
Data Sources & References
Source Type | Location | Description
Store Type Definition | 01_Build_Templates/store_types.json | type_id: prototype_innovation
Base Template | 01_Build_Templates/base_template.json | Category structure and specifications
Historical Projects | 03_Historical_Projects/historical_projects.csv | Filtered by store_type = prototype_innovation
Cost Model | 05_Cost_Models/cost_model_suburban_standard.json | Detailed line item costs and formulas
Regional Modifiers | 04_Regional_Modifiers/regional_modifiers.csv | Market-specific multipliers
Vendor Pricing | 06_Vendor_Data/vendor_pricing.csv | Current vendor unit costs
Meeting Transcripts | 07_Conversations/meeting_transcripts/vendor_negotiation/* | Pricing discussions and negotiations
Teams Conversations | 07_Conversations/teams_channels/construction-vendors.json | Vendor performance and cost insights
Calculation Formulas
Regional Adjustment | base_cost × regional_modifier | See 04_Regional_Modifiers
Timeline Premium | base_cost × (1 + premium_rate) | 15% for accelerated schedules
Total Cost | Σ(categories) × regional_modifier × timeline_factor | Compound adjustments

## Agent Instructions
AI Agent Usage Instructions
Purpose | This budget plan provides a complete cost example for Prototype/Innovation stores based on historical project data.
How to Use | 1. Review Executive Summary for high-level cost breakdown
2. Reference Detailed Line Items for specific cost components
3. Compare Scenario Comparisons to understand cost impacts of variations
4. Cite Data Sources when referencing this budget in agent responses
Adjusting for New Projects | Parameters to customize:
- Square footage (multiply line items proportionally)
- Regional market (apply regional_modifiers from folder 04)
- Timeline (apply 15% premium for accelerated schedules)
- Constraints (reference folder 02 for cost impacts)
Validation Checkpoints | Before using this budget plan:
✓ Confirm store type matches project requirements
✓ Verify square footage is within typical range
✓ Check regional modifiers are current
✓ Review recent vendor negotiations for pricing updates
Source Attribution | When citing this budget in responses:
'Based on Budget_Plan_prototype_innovation_4000sqft.xlsx
which analyzes historical Prototype/Innovation store costs'
Named Ranges | Key data zones (for programmatic access):
- CostSummary: Executive Summary!B6:D13
- LineItemsData: Detailed Line Items!A4:G[last_row]
- ScenarioCompare: Scenario Comparisons!A4:E9
Updates | To maintain accuracy:
- Regenerate quarterly as new projects complete
- Update vendor pricing after negotiations
- Adjust regional modifiers annually