## Fast Track Strategy
Fast-Track Build Strategy
Timeline Compression Techniques and Cost Impacts
STRATEGY OVERVIEW
Objective | Reduce 12-week standard timeline to 8 weeks
Primary Driver | Accelerated store opening for critical locations
Cost Impact | +15% to +20% total project cost
Risk Level | Medium-High (productivity loss, quality control)
Success Rate | 78% on-time completion (vs. 87% standard)
COST IMPACT BY CATEGORY
Category | Standard Cost | Premium | Fast-Track Cost | Justification
Construction | 226625 | 18% | 267417 | Overtime labor, weekend shifts
Electrical | 77700 | 15% | 89355 | Premium electrician rates, expedited materials
HVAC | 51800 | 12% | 58016 | Expedited delivery, installation coordination
Plumbing | 32375 | 15% | 37231 | Premium labor rates for compressed schedule
Fixtures | 161875 | 8% | 174825 | Air freight for fixtures, rush orders
Technology | 51800 | 5% | 54390 | Standard pricing (minimal timeline impact)
Soft Costs | 45325 | 10% | 49857 | Expedited permitting, additional oversight
TOTAL | 647500 | 12.91% | 731091
WHEN TO USE THIS STRATEGY
✓ Critical market entry timing (seasonal, competitive)
✓ Lease penalty clauses for delayed opening
✓ Budget can absorb 15-20% premium
✓ Vendor capacity available for compressed schedule
✓ Permitting expedite services available in jurisdiction
✗ Complex site conditions (use standard timeline)
✗ Landlord restrictions on after-hours work
✗ Tight budget constraints (consider phased approach instead)
HISTORICAL PROJECT EXAMPLES
Store ID | Market | Actual Timeline | Cost Premium | Outcome
Store-147 | Columbus | 8.5 weeks | 17% | Success - opened on time
Store-162 | Cincinnati | 9 weeks | 19% | Delayed 1 week due to permit
Store-183 | Cleveland | 8 weeks | 16% | Success - under budget